## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Green
Simplifying Medical Test Results
| Company name | Party of One?
| Project lead | Lupe Hernnadez
| Project start date: | 2024-09-16 | [10 empty] | Scrolling increment: | [5 empty] | 13
| Milestone marker: | 1 | 1 |  |  | September | [6 empty] | October | [27 empty] | November
 | time axis 2024-09-29 to 2024-11-23
| Milestone description | Assigned to | Progress | Start | Days | time axis 2024-09-29 to 2024-11-23
Proposal
| LLM Research |  | 100% | 2024-10-03 | 5
c | Project Diagrams |  | 100% | 2024-10-17 | 1 | bar: 2024-10-17
c | Write Proposal |  | 100% | 2024-09-16 | 12
LLM Testing
| Use LLM for summaries |  | 100% | 2024-10-01 | 3
| Different level summaries |  | 100% | 2024-10-03 | 1 | bar: 2024-10-03
EHR Implementation
| Add LLM's to OpenEMR |  | 0% | 2024-10-03 | 14
| Upload patient information |  | 0% | 2024-10-17 | 1 | bar: 2024-10-17
| Test LLM for patient info |  | 0% | 2024-10-17 | 14
Additional Features
| Add Verification option |  | 0% | 2024-11-12 | 15
| Update format |  | 0% | 2024-11-14 | 5
| Test Features |  | 0% | 2024-11-22 | 5
Present Project
| Create PowerPoint |  | 0% | 2024-11-24 | 10
| Final review |  | 0% | 2024-12-05 | 2

## Blue
Project title
Company name
Project lead
Project start date: | 2024-10-13 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | October | [6 empty] | November | [34 empty] | December
 | time axis 2024-10-26 to 2024-12-20
Milestone description | Assigned to | Progress | Start | Days | time axis 2024-10-26 to 2024-12-20
Title 1
Task 1 |  | 25% | 2024-10-16 | 3
Task 2 |  |  | 2024-10-21 | 1
Task 3 |  | 50% | 2024-10-13 | 10
Task 4 |  |  | 2024-11-05 | 1 | bar: 2024-11-05
Task 5 |  | 10% | 2024-10-22 | 6
Title 2
Task 1 |  | 60% | 2024-10-22 | 13
Task 2 |  | 50% | 2024-10-23 | 9
Task 3 |  | 33% | 2024-10-31 | 11
Task 4 |  |  | 2024-11-09 | 1 | bar: 2024-11-09
Task 5 |  |  | 2024-11-10 | 24
Title 3
Task 1 |  |  | 2024-10-31 | 4
Task 2 |  |  | 2024-11-04 | 14
Task 3 |  |  | 2024-11-20 | 6
Task 4 |  |  | 2024-12-03 | 3
Task 5 |  |  | 2024-11-25 | 19
Title 4
Task 1 |  |  | 2024-11-22 | 15
Task 2 |  |  | 2024-11-14 | 5
Task 3 |  |  | 2025-01-04 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project title
Company name
Project lead
Project start date: | 2024-10-13 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | October | [6 empty] | November | [34 empty] | December
 | time axis 2024-10-26 to 2024-12-20
Milestone description | Assigned to | Progress | Start | Days | time axis 2024-10-26 to 2024-12-20
Title 1
Task 1 |  | 25% | 2024-10-16 | 3
Task 2 |  |  | 2024-10-21 | 1
Task 3 |  | 50% | 2024-10-13 | 10
Task 4 |  |  | 2024-11-05 | 1 | bar: 2024-11-05
Task 5 |  | 10% | 2024-10-22 | 6
Title 2
Task 1 |  | 60% | 2024-10-22 | 13
Task 2 |  | 50% | 2024-10-23 | 9
Task 3 |  | 33% | 2024-10-31 | 11
Task 4 |  |  | 2024-11-09 | 1 | bar: 2024-11-09
Task 5 |  |  | 2024-11-10 | 24
Title 3
Task 1 |  |  | 2024-10-31 | 4
Task 2 |  |  | 2024-11-04 | 14
Task 3 |  |  | 2024-11-20 | 6
Task 4 |  |  | 2024-12-03 | 3
Task 5 |  |  | 2024-11-25 | 19
Title 4
Task 1 |  |  | 2024-11-22 | 15
Task 2 |  |  | 2024-11-14 | 5
Task 3 |  |  | 2025-01-04 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one